## How To Use
ParentProof - 26-Week Day-by-Day Marketing Plan (Delhi NCR)
Window | Tue 28 Jul 2026 to Mon 25 Jan 2027 (182 days). Ends 3 weeks before CBSE boards begin (~14 Feb 2027) - peak willingness-to-pay.
Goal | Rs 1.05 crore gross revenue: ~7,195 direct (D2C) payers + ~2,840 children via tuition/school partners (B2B2C).
How to work it | Each morning open the Day-by-Day tab, filter to today's date, do the tasks, log the KPI actual in the last column. Sunday/Monday rows contain the weekly review.
Weeks run Tue-Mon | Because the plan starts Tuesday. Positions 5-6 of each week are Sat/Sun - ground events and webinars live there deliberately.
Non-negotiables | 1) Reply to every lead within 15 minutes. 2) Log every objection verbatim. 3) Weekly review every Monday - no skips. 4) Never fake scarcity; real deadlines only.
The one metric | Weekly paying families vs target (Weekly Themes tab, col G-H). Everything else is diagnosis.
Companion files | 03 = revenue/budget model (edit blue cells). 04 = outreach trackers (schools/tuition/RWA/influencers). 05 = scripts, ad copy, content calendar, objection handling.
About the spend columns | The Day-by-Day 'Indicative day spend' is a rough guide for that day's activity (a boost, an event fee) - it is NOT the budget and does not sum to it. The authoritative budget lives in file 03. The Weekly Themes ad-spend column is derived by formula (payers x paid-ad share x CAC) and matches file 03 exactly.
Assumption | All targets assume you (founder) work this full-time with 1 intern from Oct and 2 from Dec. Numbers from the model in 03; sources cited there.

## Day-by-Day
Date | Day | Week | Phase | Weekly Theme | Special | Focus | Tasks (do all) | Primary Channel | KPI Target | Indicative day spend (Rs) | Actual / Notes
28 Jul 2026 | Tue | 1 | P0 Foundation | Set up the machine |  | Infra | - Create WhatsApp Business account (catalog, quick replies, labels) - Set up UTM/link-tracking sheet - Business email on your domain | WhatsApp/Infra | WA Business live | 0
29 Jul 2026 | Wed | 1 | P0 Foundation | Set up the machine |  | Offer & payments | - Lock pricing story: Core Rs999/6mo, Annual Rs1,799, pilot early-bird Rs749 - Put Razorpay LIVE keys on server, run one real Rs1 payment end-to-end | Product | Live payment verified | 100
30 Jul 2026 | Thu | 1 | P0 Foundation | Set up the machine |  | Seed list | - List 100 known parents from contacts/society/school groups - Tag each: class (8/9/10), area, board, warmth (hot/warm/cold) | Own network | 100-name sheet complete | 0
31 Jul 2026 | Fri | 1 | P0 Foundation | Set up the machine |  | Install surface | - Polish PWA/install page: 5 screenshots, 30-sec phone-shot demo video - Write 2 landing headline variants to A/B later | Web | Install page live | 0
01 Aug 2026 | Sat | 1 | P0 Foundation | Set up the machine |  | Content batch #1 | - Shoot 10 raw phone clips: the ASER hook ('55% of Class 5 kids can't read a Class 2 text - would you know?'), your founder story, 1-min product walkthrough | Instagram/YT | 10 clips in bank | 0
02 Aug 2026 | Sun | 1 | P0 Foundation | Set up the machine |  | Inner-circle soft launch | - Get 20 installs from family/friends - Sit beside 3 of them during onboarding; write down every hesitation | Own network | 20 installs + friction notes | 0
03 Aug 2026 | Mon | 1 | P0 Foundation | Set up the machine |  | Fix & ad rails | - Fix top 5 onboarding frictions found yesterday - Create Meta Business Manager, install pixel/CAPI - Create IG + YouTube channels | Infra | Ad account ready | 0
04 Aug 2026 | Tue | 2 | P0 Foundation | Lists & ammo |  | Target universe | - Fill 04_Outreach_Trackers: 25 schools, 30 tuition centres, 20 societies with names/areas (seed lists provided) | BD | 75 targets logged | 0
05 Aug 2026 | Wed | 2 | P0 Foundation | Lists & ammo |  | Pitch materials | - Draft 10-slide school/tuition pitch deck + 1-page PDF (Hindi + English): 'independent audit, not another tuition' | BD | Deck + one-pager done | 0
06 Aug 2026 | Thu | 2 | P0 Foundation | Lists & ammo |  | Group recon | - Join 15 parent FB/WhatsApp groups (Gurgaon Moms, Noida parents, society groups) - Read rules, note admins - DO NOT post yet | Communities | 15 groups joined | 0
07 Aug 2026 | Fri | 2 | P0 Foundation | Lists & ammo |  | Pilot invites 1 | - Send personal 1:1 pilot invite (script in 05) to first 30 of your 100-list - no broadcast, individually typed feel | WhatsApp 1:1 | 30 sent / 10 replies | 0
08 Aug 2026 | Sat | 2 | P0 Foundation | Lists & ammo |  | Pilot onboarding day | - Onboard 10 pilot parents on 15-min calls; watch the child take the first test live - Note confusion points | 1:1 calls | 10 activated pilots | 0
09 Aug 2026 | Sun | 2 | P0 Foundation | Lists & ammo |  | Pilot invites 2 | - Message next 40 from the 100-list - Evening: talk to 5 parents at your own society park about kids' studies (listen 80%) | WhatsApp 1:1 | 40 sent | 0
10 Aug 2026 | Mon | 2 | P0 Foundation | Lists & ammo |  | Referral rails | - Configure referral mechanic: unique share code per parent, reward = 1 month extension per paying referral - Test end-to-end | Product | Referral flow live | 0
11 Aug 2026 | Tue | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | Pilot care | - Call all 10 first pilots: collect verbatim reactions (these become ad copy) - Fix the week's top bug same-day | 1:1 calls | 10 calls logged | 0
12 Aug 2026 | Wed | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | Fill the pilot | - Send remaining 30 invites (100 total) - Start daily WhatsApp Status routine (1 value post/day, no selling 6 of 7 days) | WhatsApp | 25+ active pilots | 0
13 Aug 2026 | Thu | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | I-Day campaign prep | - Build 'Azaadi from tuition guesswork' creative + early-bird offer page (Rs749, first 100 families, ends Aug 31) | Creative | Campaign assets ready | 0
14 Aug 2026 | Fri | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | First group seeding | - Post value-first story in 3 parent groups: 'I checked my kid against ASER benchmarks - what I found' - Reply to every comment | FB/WA groups | 3 posts, 20+ comments | 0
15 Aug 2026 | Sat | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day | INDEPENDENCE DAY | INDEPENDENCE DAY LAUNCH | - Launch early-bird across Status + groups + IG + personal broadcast to 100-list - Reply to every single response within 15 min | All organic | First 5 payments | 500
16 Aug 2026 | Sun | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | Society event #1 | - Table at your OWN society park/club: 20 live audits on a tablet, parents see the result in 20 min - Collect numbers | Ground event | 20 audits, 10 installs | 1000
17 Aug 2026 | Mon | 3 | P1 Pilot & Proof | Pilot sprint + Independence Day |  | Objection mining | - 1:1 follow-up with every I-Day clicker who didn't pay - Log objections VERBATIM into 05 objection sheet | WhatsApp 1:1 | 10 conversations logged | 0
18 Aug 2026 | Tue | 4 | P1 Pilot & Proof | Proof factory |  | Testimonial harvest | - Ask 10 happiest pilots for a 30-sec phone video (send them the 3-line script); offer 3 months free for it | 1:1 | 3 videos received | 0
19 Aug 2026 | Wed | 4 | P1 Pilot & Proof | Proof factory |  | Case study #1 | - Write before/after story: child's predicted score, the exact weak chapter found, what the fix plan changed - 1-page PDF + carousel | Content | Case study #1 shipped | 0
20 Aug 2026 | Thu | 4 | P1 Pilot & Proof | Proof factory |  | Tuition pitch round 1 | - Walk into 3 tuition centres (Laxmi Nagar / Preet Vihar): rev-share pitch Rs200/child - Leave one-pagers | B2B field | 3 pitched, 1 verbal yes | 200
21 Aug 2026 | Fri | 4 | P1 Pilot & Proof | Proof factory |  | Founder distribution | - Post case study in 5 parent groups + LinkedIn founder post: 'What auditing 30 Delhi kids taught me' | Groups/LinkedIn | 5,000 reach | 0
22 Aug 2026 | Sat | 4 | P1 Pilot & Proof | Proof factory |  | Society event #2 | - Neighbouring society via RWA contact (Dwarka/Rohini): 20 live audits - Bring a happy pilot parent along | Ground event | 15 installs, 3 payments | 1500
23 Aug 2026 | Sun | 4 | P1 Pilot & Proof | Proof factory |  | Content factory | - Cut testimonial videos into 3 reels - Schedule the whole week's content in one sitting | Instagram | 3 reels live | 0
24 Aug 2026 | Mon | 4 | P1 Pilot & Proof | Proof factory |  | Weekly review #1 | - Funnel vs plan; pick the #1 objection and write its counter - Call 5 stalled pilots personally | Ops | Review memo done | 0
25 Aug 2026 | Tue | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Payment asks | - 1:1 payment ask to every activated pilot (30+): early-bird Rs749 closes Sunday - honest deadline, no fake scarcity | WhatsApp 1:1 | 8 payments | 0
26 Aug 2026 | Wed | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Referral activation | - Ask every paying parent: 'which 3 parents in the class group worry most about marks?' - Send them intro template | Referral | 15 referred installs | 0
27 Aug 2026 | Thu | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Partner #1 goes live | - Launch first tuition partner: poster at centre + demo day; onboard first 10 children under partner pricing | B2B | Partner #1 live | 500
28 Aug 2026 | Fri | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) | Raksha Bandhan | Raksha Bandhan touch | - Light day (Rakhi): one status - 'gift your niece/nephew a real check-up' - Confirm weekend event logistics | WhatsApp | 1 status, event locked | 0
29 Aug 2026 | Sat | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Society event #3 | - Event where pilot parents cluster (Noida/Dwarka): happy customer speaks, you demo - 20 audits | Ground event | 20 audits | 1500
30 Aug 2026 | Sun | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Early-bird close-out | - 24-hours-left broadcast + individual nudges to every fence-sitter | WhatsApp | 10 weekend payments | 0
31 Aug 2026 | Mon | 5 | P1 Pilot & Proof | Convert the pilot (early-bird closes) |  | Pilot retro | - Compute: activation rate, pilot->paid %, best-performing message - Write September ads brief USING parent verbatims | Ops | Ads brief locked | 0
01 Sep 2026 | Tue | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Meta ads launch | - Launch 5 creatives (testimonial / ASER stat / board predictor / tuition-waste / report-card shock) x 2 audiences (NCR moms 30-45, dads 35-50) @ Rs1,500/day | Meta ads | Ads live, CPI < Rs120 | 1500
02 Sep 2026 | Wed | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Lead funnel | - Wire ad leads into WhatsApp funnel: auto-reply -> 2-min demo video -> free audit link - Measure lead->install % | WhatsApp | Funnel live | 1500
03 Sep 2026 | Thu | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Teachers' Day prep | - Creative: 'Your child's teacher has 40 kids. You have one.' - Co-marketing kit for partner tuition teachers | Creative | Assets ready | 1500
04 Sep 2026 | Fri | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Tuition round 2 | - Pitch 5 centres (Rohini Sec 7 & 24 / Pitampura) with partner #1 results as proof | B2B field | 5 pitched | 1700
05 Sep 2026 | Sat | 6 | P2 Channel Testing | Ads on + Teachers' Day | TEACHERS' DAY | TEACHERS' DAY | - Publish campaign; partner centres post co-branded creative; boost best organic post Rs2,000 | All | 300 landing visits | 3500
06 Sep 2026 | Sun | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Ad triage | - Kill creatives with CTR < 0.8%; double budget on top 2; write 3 new hooks from ad comments | Meta ads | CPI <= Rs90 | 1500
07 Sep 2026 | Mon | 6 | P2 Channel Testing | Ads on + Teachers' Day |  | Weekly review #2 | - Cohort check: are W3-5 payers using it weekly? Fix #1 onboarding drop-off | Ops | Review + fix shipped | 1300
08 Sep 2026 | Tue | 7 | P2 Channel Testing | Half-yearly exam angle |  | Half-yearly campaign | - Launch 'Is your child half-yearly ready?' free 20-min audit angle across ads + groups | Meta ads | 50 leads | 1500
09 Sep 2026 | Wed | 7 | P2 Channel Testing | Half-yearly exam angle |  | Influencer outreach | - DM 20 NCR parenting creators (5k-50k followers): free Annual + Rs2-5k per reel - Track in 04 tracker | Influencers | 20 DMs, 5 replies | 1500
10 Sep 2026 | Thu | 7 | P2 Channel Testing | Half-yearly exam angle |  | School outreach begins | - Email + call 10 school coordinators: free 'reading your child's report card' parent workshop post-half-yearly | Schools | 10 contacted, 2 meetings | 1500
11 Sep 2026 | Fri | 7 | P2 Channel Testing | Half-yearly exam angle |  | Retargeting on | - Retarget installers who never finished test #1 (pixel audience) with a 'finish the audit' creative | Meta ads | +15% activation | 1500
12 Sep 2026 | Sat | 7 | P2 Channel Testing | Half-yearly exam angle |  | Partner demo day #2 | - Demo day at tuition partner; onboard 15 children; shoot content on-site (with consent) | B2B | 15 B2B children | 1500
13 Sep 2026 | Sun | 7 | P2 Channel Testing | Half-yearly exam angle |  | Objections -> content | - Batch 5 reels answering the week's top parent questions verbatim | Instagram | 5 reels | 1500
14 Sep 2026 | Mon | 7 | P2 Channel Testing | Half-yearly exam angle |  | Weekly review #3 | - Final influencer shortlist (8); send product access + brief - Review CAC by channel | Ops | 8 briefs sent | 1500
15 Sep 2026 | Tue | 8 | P2 Channel Testing | Exam week presence |  | Revision broadcasts | - During half-yearly week: free 'tonight's revision priority' daily tip broadcast (opt-in) - pure value, builds list | WhatsApp | 200 broadcast subs | 1700
16 Sep 2026 | Wed | 8 | P2 Channel Testing | Exam week presence |  | Influencers live | - First 2 influencer reels go live; track coupon-code redemptions per creator | Influencers | 2 live, 30 installs | 1700
17 Sep 2026 | Thu | 8 | P2 Channel Testing | Exam week presence |  | Tuition round 3 | - Pitch 5 centres (Indirapuram / Vaishali); close partners #3-4 | B2B field | 2 signed (4 total) | 1700
18 Sep 2026 | Fri | 8 | P2 Channel Testing | Exam week presence |  | Predictor creative | - New ad: 'We predict the half-yearly score BEFORE results' with receipt screenshots | Meta ads | CPI <= Rs80 | 1700
19 Sep 2026 | Sat | 8 | P2 Channel Testing | Exam week presence |  | Society event | - Big Indirapuram society (Shipra Riviera / ATS Advantage): 25 live audits | Ground event | 25 audits | 2500
20 Sep 2026 | Sun | 8 | P2 Channel Testing | Exam week presence |  | Prediction receipts | - Get 20 pilot parents to LOCK a predicted score before results day; screenshot each (proof bank for W9) | Product | 20 predictions locked | 1000
21 Sep 2026 | Mon | 8 | P2 Channel Testing | Exam week presence |  | Weekly review #4 | - Mid-Sept checkpoint: on pace for 100 payers/wk by W9? If not, decide the one thing to change | Ops | Decision memo | 1700
22 Sep 2026 | Tue | 9 | P2 Channel Testing | Results shock v1 |  | Results-shock launch | - Half-yearly results land: 'Result surprised you? It shouldn't have.' across every channel | All | 80 leads | 1700
23 Sep 2026 | Wed | 9 | P2 Channel Testing | Results shock v1 |  | Accuracy proof post | - Publish prediction receipts: 'X of Y predictions within 8%' - your single biggest trust asset | All organic | 10,000 reach | 1700
24 Sep 2026 | Thu | 9 | P2 Channel Testing | Results shock v1 |  | Convert the shocked | - Personal WhatsApp voice note to every activated non-payer: their result vs what the audit showed | 1:1 | 15 payments | 1700
25 Sep 2026 | Fri | 9 | P2 Channel Testing | Results shock v1 |  | Influencer wave | - 3 more reels live; whitelist best performer as Spark ad (creator's handle, your budget) | Influencers | Spark ad live | 1700
26 Sep 2026 | Sat | 9 | P2 Channel Testing | Results shock v1 |  | Double event day | - Two simultaneous society events (Gurgaon + Noida) - recruit 1 helper/intern for the second table | Ground events | 40 audits | 3000
27 Sep 2026 | Sun | 9 | P2 Channel Testing | Results shock v1 |  | Referral contest #1 | - Announce: top 3 referrers this month win Rs5,000 term-fee voucher - Leaderboard in 04 | Referral | 50 shares | 1200
28 Sep 2026 | Mon | 9 | P2 Channel Testing | Results shock v1 |  | MONTHLY deep review | - CAC by channel, cohort retention, kill/scale calls - Decide: hire 1 field intern for Oct-Jan? | Ops | October plan locked | 1000
29 Sep 2026 | Tue | 10 | P3 Double Down | Double down on what works |  | Scale winners | - Winning channel gets +50% budget; freeze everything with CAC > Rs800 | Meta ads | 150 installs/day | 2200
30 Sep 2026 | Wed | 10 | P3 Double Down | Double down on what works |  | School meetings | - Run meetings booked from W7: propose free auditorium workshop 'How to read your child's report card' | Schools | 1 workshop booked | 2200
01 Oct 2026 | Thu | 10 | P3 Double Down | Double down on what works |  | PTM gate presence | - PTM season: flyer + QR outside 5 school gates on PTM days (intern + you; check school calendars in tracker) | Ground | 200 QR scans | 2200
02 Oct 2026 | Fri | 10 | P3 Double Down | Double down on what works |  | YouTube long-form #1 | - Publish: 'CBSE Class 10 Maths - the 5 chapters that decide 60% of the paper' (evergreen SEO asset) | YouTube | Video live | 2000
03 Oct 2026 | Sat | 10 | P3 Double Down | Double down on what works |  | Partner demo days | - Partners #5-6 launch demo days; 30 children onboarded | B2B | 30 B2B children | 2200
04 Oct 2026 | Sun | 10 | P3 Double Down | Double down on what works |  | Creative refresh | - 3 new ad variants from this week's winners - Content bank refill | Meta ads | Bank full | 2200
05 Oct 2026 | Mon | 10 | P3 Double Down | Double down on what works |  | Weekly review #5 | - Check refund/complaint rate (<2%) - NPS ping to all payers | Ops | NPS >= 50 | 2000
06 Oct 2026 | Tue | 11 | P3 Double Down | School workshops |  | School workshop #1 | - Run it: 20-min talk + live audit demo + QR opt-in (goal 100 parents) | Schools | 100 opt-ins | 2200
07 Oct 2026 | Wed | 11 | P3 Double Down | School workshops |  | Opt-in drip | - Day-1 nurture to workshop opt-ins: value message + free audit link (5-message sequence in 05) | WhatsApp | 40 installs | 2200
08 Oct 2026 | Thu | 11 | P3 Double Down | School workshops |  | Press pitch | - Mail 10 education reporters (HT, TOI Delhi, IE, Dainik Jagran, Radio City/Mirchi) the accuracy-proof story | PR | 2 conversations | 2200
09 Oct 2026 | Fri | 11 | P3 Double Down | School workshops |  | Dussehra arc prep | - Build 'burn the guesswork' Dussehra->Diwali creative arc (10 assets) | Creative | Assets ready | 2200
10 Oct 2026 | Sat | 11 | P3 Double Down | School workshops |  | Event + workshop #2 | - Saturday: society event AND school workshop #2 (split team) | Ground/Schools | 120 combined opt-ins | 2500
11 Oct 2026 | Sun | 11 | P3 Double Down | School workshops |  | Case study #3 | - On-camera interview with a paying parent (their words, their kitchen) - Cut into reel + PDF | Content | Case study #3 | 1400
12 Oct 2026 | Mon | 11 | P3 Double Down | School workshops |  | Weekly review #6 | - Publish internal scoreboard: cumulative revenue vs Rs1Cr trajectory line | Ops | On-track check | 1300
13 Oct 2026 | Tue | 12 | P3 Double Down | Pre-Dussehra push |  | Festive offer live | - Diwali-quarter pricing: Annual Rs1,499 (vs 1,799), deadline Nov 9 - anchor everywhere | All | Offer live | 2500
14 Oct 2026 | Wed | 12 | P3 Double Down | Pre-Dussehra push |  | Festive ad test | - 3 festive creative variants; +Rs1,000/day budget | Meta ads | CPI <= Rs75 | 2600
15 Oct 2026 | Thu | 12 | P3 Double Down | Pre-Dussehra push |  | Faridabad B2B | - Pitch 5 centres (Faridabad Sec 15/16); partners co-broadcast to their parent lists | B2B | 2 signed (6-8 total) | 2500
16 Oct 2026 | Fri | 12 | P3 Double Down | Pre-Dussehra push |  | Founder op-ed | - LinkedIn/Medium: 'Parents pay Rs5,000/mo for tuition and Rs0 to check it works' - Press follow-ups | PR | 1 pickup | 2500
17 Oct 2026 | Sat | 12 | P3 Double Down | Pre-Dussehra push |  | Dussehra mela #1 | - Booth at big society mela (Gaur City / Noida Ext) - highest-footfall day of the season | Ground event | 60 audits | 3500
18 Oct 2026 | Sun | 12 | P3 Double Down | Pre-Dussehra push |  | Dussehra mela #2 | - Second mela booth (Dwarka sector mela) | Ground event | 50 audits | 3000
19 Oct 2026 | Mon | 12 | P3 Double Down | Pre-Dussehra push |  | Weekly review #7 | - Lock Dussehra-week logistics; stock QR standees, tablets charged, intern briefed | Ops | Logistics locked | 1400
20 Oct 2026 | Tue | 13 | P3 Double Down | Dussehra week | DUSSEHRA | DUSSEHRA | - 'Burn the guesswork' day: greeting broadcast AM (no sell), offer push PM; top testimonial ad on max | All | 25 payments today | 3000
21 Oct 2026 | Wed | 13 | P3 Double Down | Dussehra week |  | Mela lead conversion | - Every mela lead gets 1:1 follow-up within 48h (voice note > text) | WhatsApp 1:1 | 30% lead->install | 2500
22 Oct 2026 | Thu | 13 | P3 Double Down | Dussehra week |  | School workshops #3-4 | - Post-Dussehra school slots; same format, tighter script | Schools | 200 opt-ins | 2500
23 Oct 2026 | Fri | 13 | P3 Double Down | Dussehra week |  | Accuracy update #2 | - Publish bigger-N accuracy post; refresh every ad's proof line | All organic | Post live | 2500
24 Oct 2026 | Sat | 13 | P3 Double Down | Dussehra week |  | Gift cards live | - Launch Diwali gift card ('gift an audit to cousins/nieces') + society event | Product/Ground | Gift card live | 2500
25 Oct 2026 | Sun | 13 | P3 Double Down | Dussehra week |  | Diwali content batch | - 6 Diwali-arc assets: family pride angle - 'This Diwali, give them being seen' | Creative | 6 assets | 2500
26 Oct 2026 | Mon | 13 | P3 Double Down | Dussehra week |  | MONTHLY review | - October cohorts, CAC <= Rs550? - Lock November (biggest month) plan + budgets | Ops | Nov plan locked | 2500
27 Oct 2026 | Tue | 14 | P4 Diwali & Reset | Diwali ramp |  | Diwali campaign live | - Annual Rs1,499 countdown (13 days) on homepage, ads, partner centres | All | 40 Annual sales/wk | 3000
28 Oct 2026 | Wed | 14 | P4 Diwali & Reset | Diwali ramp |  | Book mela booths | - Lock 4 society Diwali-mela booths for Nov 1-8 window (RWA tracker calls) | Ground | 4 booked | 3000
29 Oct 2026 | Thu | 14 | P4 Diwali & Reset | Diwali ramp |  | Retarget everyone | - Every installed non-payer gets Diwali offer via WhatsApp + retargeting ads | Meta ads/WA | 5% convert | 3000
30 Oct 2026 | Fri | 14 | P4 Diwali & Reset | Diwali ramp |  | Influencer wave #2 | - Book 5 creators for Diwali-themed reels ('between crackers and sweets - 20 minutes of truth') | Influencers | 5 booked | 3000
31 Oct 2026 | Sat | 14 | P4 Diwali & Reset | Diwali ramp |  | Mela booth (Gurgaon) | - DLF/Sushant Lok society mela: 70 audits target | Ground event | 70 audits | 4000
01 Nov 2026 | Sun | 14 | P4 Diwali & Reset | Diwali ramp |  | Mela booth (Indirapuram) | - Second booth; live IG stories from the ground | Ground event | 60 audits | 3500
02 Nov 2026 | Mon | 14 | P4 Diwali & Reset | Diwali ramp |  | Weekly review #8 | - Support load check: response SLA < 2h even at volume - Fix before Diwali week | Ops | SLA green | 1500
03 Nov 2026 | Tue | 15 | P4 Diwali & Reset | Diwali week (Nov 8) |  | Pre-Dhanteras | - 'Buy gold, gift certainty' creative day; all-partner co-broadcast | All | 60 payments/wk pace | 3500
04 Nov 2026 | Wed | 15 | P4 Diwali & Reset | Diwali week (Nov 8) |  | Evening booths | - Society booths Wed evening (societies lit up, families out) | Ground | 50 audits | 3500
05 Nov 2026 | Thu | 15 | P4 Diwali & Reset | Diwali week (Nov 8) |  | Evening booths + live | - Booths again + live IG coverage; UGC reposts | Ground/IG | 20,000 reach | 3500
06 Nov 2026 | Fri | 15 | P4 Diwali & Reset | Diwali week (Nov 8) | Dhanteras | DHANTERAS | - Biggest broadcast of the quarter; 2-kids family bundle (20% off second child) | All | 50 payments | 4000
07 Nov 2026 | Sat | 15 | P4 Diwali & Reset | Diwali week (Nov 8) |  | Choti Diwali | - Soft presence: greetings + 'last chance at Rs1,499' PM only | WhatsApp | 30 payments | 3000
08 Nov 2026 | Sun | 15 | P4 Diwali & Reset | Diwali week (Nov 8) | DIWALI | DIWALI - no selling | - Greetings only. Zero sell. Brand equity day. (Schedule Monday's close-out tonight) | All | Goodwill | 500
09 Nov 2026 | Mon | 15 | P4 Diwali & Reset | Diwali week (Nov 8) |  | Offer closes tonight | - Diwali price ends midnight: final countdown broadcasts + 1:1 nudges to every fence-sitter | WhatsApp | 60 payments | 3000
10 Nov 2026 | Tue | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Study reset campaign | - 'Post-Diwali study reset' free audit angle; pricing back to standard (say it plainly - builds trust) | All | 80 leads | 3000
11 Nov 2026 | Wed | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Fence-sitter convert | - Missed-Diwali converts at standard price with bonus: second child free for 1 month | WhatsApp 1:1 | 25 payments | 3000
12 Nov 2026 | Thu | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Children's Day prep | - Book school workshops #5-6 - Creative: 'The gift of being seen' | Schools | 2 workshops booked | 3000
13 Nov 2026 | Fri | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Winter B2B push | - 10 new tuition pitches (winter batch enrolment season starts) | B2B field | 3 signed (12+ total) | 3000
14 Nov 2026 | Sat | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day | CHILDREN'S DAY | CHILDREN'S DAY | - Campaign day + presence at school events | All | 300 opt-ins | 3500
15 Nov 2026 | Sun | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Diwali cohort stories | - Case studies #4-5 from Diwali buyers; content batch | Content | 2 case studies | 3000
16 Nov 2026 | Mon | 16 | P4 Diwali & Reset | Post-Diwali reset + Children's Day |  | Weekly review #9 | - Draft December pre-board plan; December = harvest month | Ops | Plan drafted | 2500
17 Nov 2026 | Tue | 17 | P4 Diwali & Reset | Winter-batch B2B |  | Partner bundles | - Winter-batch co-launch: partners bundle ParentProof into enrolment (Rs749 add-on, their margin Rs200) | B2B | 60 B2B children/wk | 3000
18 Nov 2026 | Wed | 17 | P4 Diwali & Reset | Winter-batch B2B |  | Ad fatigue fix | - Full creative refresh (frequency > 3 = fatigue); winter set live | Meta ads | CTR >= 1.2% | 3000
19 Nov 2026 | Thu | 17 | P4 Diwali & Reset | Winter-batch B2B |  | School workshops #5-6 | - Run both; QR opt-ins into pre-board nurture sequence | Schools | 250 opt-ins | 3000
20 Nov 2026 | Fri | 17 | P4 Diwali & Reset | Winter-batch B2B |  | Pre-board nurture | - 5-message pre-board WhatsApp sequence for ALL non-payers (sequence in 05) | WhatsApp | Sequence live | 3000
21 Nov 2026 | Sat | 17 | P4 Diwali & Reset | Winter-batch B2B |  | Faridabad event | - Society event (Faridabad Sec 15/21) - underserved, low competition | Ground event | 40 audits | 3500
22 Nov 2026 | Sun | 17 | P4 Diwali & Reset | Winter-batch B2B |  | 100-day series prep | - Plan '100 days to boards' daily countdown series (starts Dec 1) | Creative | Series planned | 3000
23 Nov 2026 | Mon | 17 | P4 Diwali & Reset | Winter-batch B2B |  | Weekly review #10 | - Decision: hire 2 field interns for Dec-Jan sprint? (Rs12k/mo each) - Lock W18 webinar | Ops | Decision made | 2500
24 Nov 2026 | Tue | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Predictor campaign | - Hero campaign: 'Know their board score 100 days early' - biggest creative push yet | Meta ads | 100 leads/day | 4000
25 Nov 2026 | Wed | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Webinar #1 announce | - 'The pre-board plan for Class 10 parents' with a partner tutor; WhatsApp registrations | Webinar | 200 registrations | 4000
26 Nov 2026 | Thu | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Budget +50% | - Dec-Jan is harvest: scale ads while CAC <= Rs500 - New proof creative with accuracy stats | Meta ads | Stable CAC at scale | 4500
27 Nov 2026 | Fri | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Tutor affiliates | - 10 partner tutors get 10% commission links for their parent groups | Affiliates | 5 tutors live | 4000
28 Nov 2026 | Sat | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | WEBINAR #1 (Sat 8pm) | - Run it: 25 min value, 10 min product, attendee-only same-night offer | Webinar | 25 payments | 4500
29 Nov 2026 | Sun | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Replay + follow-up | - Replay to no-shows; 1:1 to every attendee | WhatsApp | 15 payments | 3000
30 Nov 2026 | Mon | 18 | P5 Pre-Board Ramp | Pre-board ramp: predictor hero |  | Weekly review #11 | - Lock December targets (400+/wk) and team roles | Ops | Targets locked | 3000
01 Dec 2026 | Tue | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | Countdown starts | - '100 days to boards' daily series begins (IG + Status + broadcast) - runs till plan end | All organic | Daily habit installed | 4200
02 Dec 2026 | Wed | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | School workshops #7-8 | - Pre-board prep talks; heaviest opt-in weeks of the year | Schools | 300 opt-ins | 4200
03 Dec 2026 | Thu | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | Winter intensive design | - Build '2-week winter intensive audit plan' offer for the holidays | Product/Creative | Offer ready | 4200
04 Dec 2026 | Fri | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | Urgency ads | - Countdown-urgency creative; hard retarget on all warm audiences | Meta ads | 70 paid payers/wk | 4500
05 Dec 2026 | Sat | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | WEBINAR #2 (Science) | - 'Science pre-board: what to fix first' - Same offer mechanics | Webinar | 250 regs, 30 payments | 4500
06 Dec 2026 | Sun | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | Success story #6 | - Parent success reel + 3 more countdown assets | Content | 4 reels | 4200
07 Dec 2026 | Mon | 19 | P5 Pre-Board Ramp | 100-day countdown engine |  | Weekly review #12 | - Did we cross 400 payers this week? Gap analysis if not | Ops | Review done | 4200
08 Dec 2026 | Tue | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Prediction receipts at scale | - 'Pre-boards this week? Lock your prediction' - every user locks a predicted score (proof engine) | Product/All | 500 predictions locked | 4700
09 Dec 2026 | Wed | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Surround-sound day | - All 12+ partners broadcast the same day - one voice across NCR | B2B | 100 B2B leads | 4700
10 Dec 2026 | Thu | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Close partners 13-16 | - Tuition centres want retention tools for Jan batches - easiest close of the year | B2B field | 4 signed | 4700
11 Dec 2026 | Fri | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Rs99 trial experiment | - Test impulse tier: Rs99 single audit -> upgrade path to Core - Measure trial->Core % | Product/Ads | Experiment live | 4700
12 Dec 2026 | Sat | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | WEBINAR #3 (Maths) | - 'The 5 chapters that decide 60% of the Maths paper' | Webinar | 300 registrations | 4700
13 Dec 2026 | Sun | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Conversion sprint | - Team calls 100 warm leads (webinar attendees, event leads, stalled users) | 1:1 calls | 40 payments | 4500
14 Dec 2026 | Mon | 20 | P5 Pre-Board Ramp | Pre-boards begin |  | Weekly review #13 | - Rs99 experiment readout: keep or kill - W21 plan | Ops | Keep/kill decision | 4000
15 Dec 2026 | Tue | 21 | P5 Pre-Board Ramp | Mid-December push |  | Receipts proof wave | - Pre-board results wave 1: 'Surprised again?' + receipt screenshots - biggest proof week of the plan | All | Peak organic reach | 4700
16 Dec 2026 | Wed | 21 | P5 Pre-Board Ramp | Mid-December push |  | Winter intensive sales | - Break starts: sell the 2-week intensive as structured onboarding | All | 60 payments | 4700
17 Dec 2026 | Thu | 21 | P5 Pre-Board Ramp | Mid-December push |  | New Year prep | - Design 'New Year, No Surprises' Jan 1 campaign + assets | Creative | Assets ready | 4700
18 Dec 2026 | Fri | 21 | P5 Pre-Board Ramp | Mid-December push |  | Proof-led ads | - Ads rebuilt around real receipts (blur names) - CAC check | Meta ads | CAC <= Rs450 | 4700
19 Dec 2026 | Sat | 21 | P5 Pre-Board Ramp | Mid-December push |  | Winter carnival booths | - 2 society winter-carnival booths | Ground events | 80 audits | 5000
20 Dec 2026 | Sun | 21 | P5 Pre-Board Ramp | Mid-December push |  | Holiday content bank | - Batch everything for Christmas-New Year window (team goes light) | Content | Bank full | 4700
21 Dec 2026 | Mon | 21 | P5 Pre-Board Ramp | Mid-December push |  | Weekly review #14 | - Christmas-week ops: automation on, SLA plan with skeleton staff | Ops | Plan set | 4500
22 Dec 2026 | Tue | 22 | P6 Peak Conversion | Holiday harvest |  | Intensive cohort #1 | - Winter-break intensive starts: 300 kids, daily engagement pings (retention = Jan revenue) | Product | 300 in cohort | 4700
23 Dec 2026 | Wed | 22 | P6 Peak Conversion | Holiday harvest |  | Gift-card push | - Family gatherings week: 'Chachu gifts the audit' creative | All organic | 30 gift cards | 4700
24 Dec 2026 | Thu | 22 | P6 Peak Conversion | Holiday harvest |  | Christmas eve | - Light touch; automations run; team rests (you too) | Auto | SLA holds | 4000
25 Dec 2026 | Fri | 22 | P6 Peak Conversion | Holiday harvest | Christmas | Christmas | - Greetings + one strong story post. No selling | Organic | Reach | 4000
26 Dec 2026 | Sat | 22 | P6 Peak Conversion | Holiday harvest |  | 3-cousins offer | - Family-gathering referral: 3 kids together = 25% off each | Referral | 40 payments | 5000
27 Dec 2026 | Sun | 22 | P6 Peak Conversion | Holiday harvest |  | Gift activation | - 1:1 follow-up with every gift-card recipient: activate before Jan 1 | WhatsApp 1:1 | 70% activation | 4600
28 Dec 2026 | Mon | 22 | P6 Peak Conversion | Holiday harvest |  | Weekly review #15 | - New Year campaign final check; Jan targets confirmed | Ops | Ready | 5000
29 Dec 2026 | Tue | 23 | P6 Peak Conversion | New Year, No Surprises |  | 2026 report card | - Year-end proof recap: 'N children audited, X% within 8%' - post + press pitch | PR/Organic | 15,000 reach | 5100
30 Dec 2026 | Wed | 23 | P6 Peak Conversion | New Year, No Surprises |  | Resolution teaser | - NY resolution campaign teaser; retarget every warm audience | Meta ads | 150 leads/day | 5100
31 Dec 2026 | Thu | 23 | P6 Peak Conversion | New Year, No Surprises |  | NYE broadcast | - Resolution framing; offer opens at midnight | WhatsApp | Set-up done | 5100
01 Jan 2027 | Fri | 23 | P6 Peak Conversion | New Year, No Surprises | NEW YEAR | JAN 1 CAMPAIGN | - 'New Year, No Surprises' - final big Annual push of the plan | All | 80 payments | 5500
02 Jan 2027 | Sat | 23 | P6 Peak Conversion | New Year, No Surprises |  | WEBINAR #4 | - '90 days: the realistic board plan' (Sat) | Webinar | 350 registrations | 5300
03 Jan 2027 | Sun | 23 | P6 Peak Conversion | New Year, No Surprises |  | Conversion sprint | - Calls + voice notes to every registrant | 1:1 | 50 payments | 5000
04 Jan 2027 | Mon | 23 | P6 Peak Conversion | New Year, No Surprises |  | Weekly review #16 | - January = final month memo; 600+/wk targets; interns briefed | Ops | Locked | 4900
05 Jan 2027 | Tue | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | Shock campaign v2 | - Full-scale results-shock with every proof asset built since Sept | All | Peak CTR | 5600
06 Jan 2027 | Wed | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | School workshops #9-10 | - Pre-board debrief talks for parents - schools now inviting YOU | Schools | 400 opt-ins | 5600
07 Jan 2027 | Thu | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | Surround-sound #2 | - 16+ partners broadcast same day | B2B | 150 B2B leads | 5600
08 Jan 2027 | Fri | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | Max scale ads | - Scale to ceiling within CAC <= Rs450 guardrail | Meta ads | 90 paid payers/wk | 5600
09 Jan 2027 | Sat | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | Webinar #5 + event | - Both on Saturday (split team) | Webinar/Ground | 40 payments | 5600
10 Jan 2027 | Sun | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | Sunday sprint | - 1:1 conversion day | 1:1 | 50 payments | 5000
11 Jan 2027 | Mon | 24 | P6 Peak Conversion | Results shock v2 (pre-board results) |  | GAP ANALYSIS | - Revenue vs Rs1Cr: if < 80% of pace, trigger contingency levers (listed in 03 model, Scenarios tab) | Ops | Go/adjust decision | 6000
12 Jan 2027 | Tue | 25 | P6 Peak Conversion | 40 days to boards |  | 40-day urgency | - '40 days, 5 chapters' series; free daily revision-priority broadcast -> upsell | All organic | 5,000 broadcast subs | 6000
13 Jan 2027 | Wed | 25 | P6 Peak Conversion | 40 days to boards |  | Win-back | - Every churned/stalled user: personal note + restart offer | WhatsApp 1:1 | 10% win back | 6000
14 Jan 2027 | Thu | 25 | P6 Peak Conversion | 40 days to boards | Makar Sankranti | Board-sprint packages | - Partners' crash course + your audit = co-package (5 partners) | B2B | 5 packages live | 6000
15 Jan 2027 | Fri | 25 | P6 Peak Conversion | 40 days to boards |  | Final creative refresh | - Countdown timers in ads; last full refresh | Meta ads | CAC holds <= Rs450 | 6000
16 Jan 2027 | Sat | 25 | P6 Peak Conversion | 40 days to boards |  | WEBINAR #6 | - Last big webinar + society event | Webinar/Ground | 400 registrations | 6000
17 Jan 2027 | Sun | 25 | P6 Peak Conversion | 40 days to boards |  | Conversion sprint | - Full-team calling day | 1:1 | 60 payments | 6000
18 Jan 2027 | Mon | 25 | P6 Peak Conversion | 40 days to boards |  | Weekly review #17 | - Final week plan: hour-by-hour for the close | Ops | Plan set | 6000
19 Jan 2027 | Tue | 26 | P6 Peak Conversion | Final sprint |  | Capacity framing | - 'Last audit slots before boards' - honest capacity limits, no fake scarcity | All | Pace: 680 payers/wk | 6400
20 Jan 2027 | Wed | 26 | P6 Peak Conversion | Final sprint |  | All-channel day | - Every channel pushes simultaneously - record single day | All | Record day | 6400
21 Jan 2027 | Thu | 26 | P6 Peak Conversion | Final sprint |  | 50 calls/day | - Founder + team: 50 conversion calls/day all week | 1:1 | 40 payments/day | 6400
22 Jan 2027 | Fri | 26 | P6 Peak Conversion | Final sprint |  | Partner finale | - Final partner broadcasts; B2B target 240 children this week | B2B | 240 B2B children | 6400
23 Jan 2027 | Sat | 26 | P6 Peak Conversion | Final sprint |  | R-Day eve mega-webinar | - 'The 25-day board plan' - biggest webinar of the plan | Webinar | 500 registrations | 6800
24 Jan 2027 | Sun | 26 | P6 Peak Conversion | Final sprint |  | Close + thank you | - Final conversions AM; PM = thank-you campaign to every customer + referral ask | All | Strong close | 6400
25 Jan 2027 | Mon | 26 | P6 Peak Conversion | Final sprint |  | PLAN RETRO | - Total vs Rs1Cr - Cohort LTV - Write next-90-days plan: boards -> results season -> Class 9 upsell | Ops | Retro + next plan | 6000

## Weekly Themes
Week | Dates | Phase | Theme | D2C Payers Target | B2B Children Target | Paid CAC (Rs) | Ad Spend (Rs) | Other Spend (Rs) | Revenue Target (Rs) | Cumulative (Rs) | Actual Payers | Actual Revenue | Inputs
1 | 28 Jul - 03 Aug | P0 Foundation | Set up the machine | 0 | 0 | 650 |  | 3000 |  |  |  |  | D2C ARPU (Rs) | 1159
2 | 04 Aug - 10 Aug | P0 Foundation | Lists & ammo | 5 | 0 | 650 |  | 4000 |  |  |  |  | B2B per child (Rs) | 749
3 | 11 Aug - 17 Aug | P1 Pilot & Proof | Pilot sprint + Independence Day | 15 | 0 | 650 |  | 6000 |  |  |  |  | Share of payers from paid ads | 45%
4 | 18 Aug - 24 Aug | P1 Pilot & Proof | Proof factory | 25 | 0 | 650 |  | 8000
5 | 25 Aug - 31 Aug | P1 Pilot & Proof | Convert the pilot (early-bird closes) | 40 | 0 | 650 |  | 8000 |  |  |  |  | ARPU = 80% Core Rs999 + 20% Annual Rs1,799. Ad spend is DERIVED (payers x paid share x CAC) and matches file 03's Weekly Model exactly. File 03 is the source of truth for budget.
6 | 01 Sep - 07 Sep | P2 Channel Testing | Ads on + Teachers' Day | 60 | 40 | 600 |  | 9000
7 | 08 Sep - 14 Sep | P2 Channel Testing | Half-yearly exam angle | 80 | 40 | 600 |  | 12000
8 | 15 Sep - 21 Sep | P2 Channel Testing | Exam week presence | 100 | 60 | 600 |  | 12000
9 | 22 Sep - 28 Sep | P2 Channel Testing | Results shock v1 | 130 | 60 | 600 |  | 14000
10 | 29 Sep - 05 Oct | P3 Double Down | Double down on what works | 160 | 80 | 550 |  | 12000
11 | 06 Oct - 12 Oct | P3 Double Down | School workshops | 190 | 80 | 550 |  | 14000
12 | 13 Oct - 19 Oct | P3 Double Down | Pre-Dussehra push | 220 | 100 | 550 |  | 16000
13 | 20 Oct - 26 Oct | P3 Double Down | Dussehra week | 250 | 100 | 550 |  | 16000
14 | 27 Oct - 02 Nov | P4 Diwali & Reset | Diwali ramp | 280 | 120 | 500 |  | 18000
15 | 03 Nov - 09 Nov | P4 Diwali & Reset | Diwali week (Nov 8) | 300 | 120 | 500 |  | 22000
16 | 10 Nov - 16 Nov | P4 Diwali & Reset | Post-Diwali reset + Children's Day | 320 | 140 | 500 |  | 14000
17 | 17 Nov - 23 Nov | P4 Diwali & Reset | Winter-batch B2B | 340 | 140 | 500 |  | 14000
18 | 24 Nov - 30 Nov | P5 Pre-Board Ramp | Pre-board ramp: predictor hero | 360 | 160 | 480 |  | 16000
19 | 01 Dec - 07 Dec | P5 Pre-Board Ramp | 100-day countdown engine | 400 | 160 | 480 |  | 16000
20 | 08 Dec - 14 Dec | P5 Pre-Board Ramp | Pre-boards begin | 440 | 180 | 480 |  | 16000
21 | 15 Dec - 21 Dec | P5 Pre-Board Ramp | Mid-December push | 480 | 180 | 480 |  | 16000
22 | 22 Dec - 28 Dec | P6 Peak Conversion | Holiday harvest | 520 | 200 | 450 |  | 14000
23 | 29 Dec - 04 Jan | P6 Peak Conversion | New Year, No Surprises | 560 | 200 | 450 |  | 16000
24 | 05 Jan - 11 Jan | P6 Peak Conversion | Results shock v2 (pre-board results) | 600 | 220 | 450 |  | 16000
25 | 12 Jan - 18 Jan | P6 Peak Conversion | 40 days to boards | 640 | 220 | 450 |  | 16000
26 | 19 Jan - 25 Jan | P6 Peak Conversion | Final sprint | 680 | 240 | 450 |  | 18000
TOTAL